## Sheet1
Student Name | Nurse Baylor
Project Title | Implementation of "X" screening tool and referral process for patients with "X"
Project Description: What is the project? Where or what type of facility? Projected change in patient outcome or benefit to business?
Implementation of "X" screening tool and referral process for patients with or at risk for "X" at abc clinic. The projected outcome is to…
| Enter Annual Salary here | Hourly Wage. This will calculate for you. | Number of staff to be included | Total hours per year | Total Dollars (annual). This will calculate for you. | Insert rationale for including the expense. Phrases are acceptable; do not need to be complete sentences.
Personnel Time project planning meetings
DNP | 150000 | 72.1154 | 1 | 48 | 3461.5385 | Plan and lead 12 meetings /year | (4hr X 12)
Office manager | 100000 | 48.0769 | 1 | 24 | 1153.8462 | Attend and assist with 12 meetings/year | (2hr X 12)
RN | 80000 | 38.4615 | 4 | 12 | 1846.1538 | Attend 12 meetings /year | (1hr X 12)
Clerical support | 50000 | 24.0385 | 1 | 12 | 288.4615 | Attend 12 meetings /year | (1hr X 12)
IT | 80000 | 38.4615 | 1 | 72 | 2769.2308 | Attend and assist with 12 meetings/year | (6hr X12)
|  |  |  | subtotal | 9519.2308
Personnel Time training costs
DNP | 150000 | 72.1154 | 4 | 2 | 576.9231 | 4 DNPs will receive 2 hours of training
Office manager | 100000 | 48.0769 | 1 | 2 | 96.1538 | 1 Office manager will receive 2 hours of training
RN | 80000 | 38.4615 | 4 | 2 | 307.6923 | 4 RNs will receive 2 hours of training
Clerical support | 50000 | 24.0385 | 1 | 2 | 48.0769 | 1 secretary will receive 2 hours of training
| 80000 | 38.4615 |  | subtotal | 1028.8462
Personnel Time at time of implementation and for first year
DNP | 150000 | 72.1154 | 1 | 352 | 25384.6154 | 8 hrs/week for 44 weeks manage project
Office manager | 100000 | 48.0769 | 1 | 176 | 8461.5385 | 4 hrs/week for 44 weeks implement and monitor
RN | 80000 | 38.4615 | 4 | 44 | 6769.2308 | each 1 hours/week for 44 weeks implment and monitor
Clerical support | 50000 | 24.0385 | 1 | 44 | 1057.6923 | 1 hour/week for 44 weeks implmenet and monitor
|  |  |  | subtotal | 41673.0769
Supplies | [5 empty] | Provide details about each expense
Education and Training supplies |  |  |  |  | 1000 | handouts, treats
Supply equipment for project implementation and/or monitoring, e.g., technology, apps, websites, medical equipment, stationery, etc. |  |  |  |  | 0 | none needed
Rent/lease |  |  |  |  | 0 | N/A already done in existing clinic
Phone/internet |  |  |  |  | 0 | N/A already done in existing clinic
Insurance |  |  |  |  | 0 | N/A already done in existing clinic
Legal/compliance/billing |  |  |  |  | 0 | N/A already done in existing clinic
Other |  |  |  |  | 0 | N/A already done in existing clinic
|  |  |  | subtotal | 1000
|  |  | TOTAL Annual investment or cost |  | 53221.1538
Cost Savings/Avoidance -
How much does each occurrence cost? (This is the cost you are tryng to prevent, e.g., falls, infections, readmissions, etc.) |  |  |  |  | 3000 | Each occurrence of "X" costs the clinic …
How many occur per year? |  |  |  |  | 250 | "X" occurs at the clinic 4 times/month
|  |  |  | current annual cost | 750000
How many occurrences do you plan to avoid in the first year? |  |  |  |  | 25 | Reduce occurenece by 10% in the first year.
|  |  |  | expected cost avoidance | 75000
ROI
|  |  | Step 1 | Savings-investment | 21778.8462
|  |  | Step 2 | Divide by investment | 53221.1538
|  |  |  | Projected ROI | 40.92%